## Product
Description | Notes | Developer Notes | Story Points | Signed | Whose Job? | Finished
As a product owner, I need to a proposal to make sure the product is worth investing in. | /doc/proposal.md |  | 3 | Team Rocket | Jonathon | TRUE
As a developer, I need to add a project board to my github repo. |  |  | 0 | Team Rocket | Xavier | TRUE
As a developer, I need to an organized plan for the development process. | /doc/organization.md |  | 1 | Team Rocket | Dale | TRUE
As a developer, I would like a file with the authors to know who wrote the code in this project. | AUTHORS file - Just a basic file with our names |  | 0 | Team Rocket | Dale | TRUE
As a product owner, I want a license to reserve rights to my product. | LICENSE file - MIT License |  | 0 | Team Rocket | Jonathon | TRUE
As a developer, I would like a file with a simple explanation for the project. | README.md |  | 1 | Team Rocket | Ryan | TRUE
As a developer, I need to a .gitignore file to ensure that the only files uploaded to the remote repository are the ones that should be uploaded. | .gitignore file - Use the gitignore resource in the sprint1 assignment |  | 0 | Team Rocket | Xavier | TRUE
As a developer, I need a system to test my code within this project. | Needs some pretend tests | JUnit | 3 | Team Rocket | Xavier | TRUE
As a developer, I need a build system to build the project. | Gradle |  | 3 | Team Rocket | Xavier | TRUE
As a product owner, I would like to see a prototype of the project. | - Terminal Based - Rabbits - Output to terminal - Animal movement - Cloning - Breeding time configuration | - Simulation Class - Animal Abstract Class - - Move method - - Breed method - Rabbit Abstract Class - Terminal Output Handler | 8 | Team Rocket | Team Rocket | TRUE
As a user, I would like foxes to have to hunt rabbits. | Foxes should breed daily and eat rabbits. If they don't eat enough, they can't breed and may die. | Fox.java is a subclass of AbstractAnimal.java | 2 | Team Rocket | Ryan | TRUE
As a user, I would like rabbits to have to eat grass. | Grass should grow daily and should be more likely to grow near other grass. | Grass.java is a subclass of AbstractOrganism.java | 2 | Team Rocket | Xavier | TRUE
As a developer, I want an abstract class to streamline the development of organisms. | Should contain any methods and implementations that all organisms may use. | AbstractOrganism.java | 2 | Team Rocket | Ryan | TRUE
As a user, if Animals don't eat I want them to die. | Animals that don't eat enough food die before the next time unit | This would require changes to the animal abstract class so that all animals have a required food amount and probably the simulation class | 2 | Team Rocket | Dale Morris, John | FALSE
As a user, I want an intuitive GUI to interact with the simulation. | The environment map should have a graphical display that is easy to understand/interpret. |  | 30 |  |  | FALSE
As a user, I want to be able to apply a localization file to the program. | Have some sort of language directory that contains localization files. Give user's the ability to add or create a language file to this directory, and then allow them to change the file in the config so that all user-facing messages are grabbed from the new language file rather then the default (english) one. | Would need some translation class, and then a way to grab the language file described from the config. All user-facing messages would need to be passed through the class. Xavier's done work like this before. | 3 |  |  | FALSE
As a user, I want to be able to configure the program | Allow user to pass a -g, -f, -r, --size flag to set the amount of animals in the inital simulation or the size of the simulation |  | 5 |  | Xavier | TRUE
As a developer I would like to reduce cucumber testing to one command, | Allow some sort of command to be run, such as ./gradlew cucumber and make it run all feature tests |  | 3 |  | Xavier | TRUE
I would also like to restrict branch merge's based upon code coverage being >90% and passing all unit tests | Also work with github applets to work with merge restrictions | Talk to professor sexton about the second part of the story | 3 |  | Xavier | TRUE
As a developer I need to add an architecture.md file |  |  | 2 |  | Dale | TRUE
As a user, I want rabbit breeding to depend on how much food they've eaten | If rabbits don't eat a certain amount of food they cannot breed |  | 2 |  | Ryan | FALSE
As a developer, I want the Simulation to contain the Map instead of internally representing it. |  | Map.java | 2 | Dale Morris, John Roberts | Dale Morris | TRUE
As a developer, I want to simplify the Simulation and defer animal-related logic to animal classes. |  | Simulation.java | 5 | Dale Morris, John Roberts | Dale Morris, John Roberts | TRUE
As a user, I would like to see foxes actively hunt rabbits. | Foxes should find the shortest path to the nearest rabbit. | Update to move() in Fox.java | 13 |  |  | FALSE
As a developer, I would like to document the end of the previous sprint and the beginning of the new one. |  |  | 2 | Xavier | Xavier | TRUE
As a user, I would like rabbits to be able to eat carrots as a new food type. | Carrots should feed rabbits more than grass. | Carrot.java extends AbstractPlant.java | 3 |  |  | TRUE
As a developer, I want to see documentation for the design patterns used in the source code. |  | doc/designpatterns.md |  |  |  | TRUE
As a user, I would like to see rainy and sunny weather states and how they interact with the simulation. | Grass should grow more quickly during rainy weather compared to sunny weather. | Write a Weather.java interface and have Rain.java and Sunshine.java implement it | 21 |  |  | FALSE
As a developer, I would like an iterator to easily iterate through a map object. |  | MapIterator.java | 3 |  |  | FALSE
As a user, I would like to see how mutations affect the survival of organisms. | Organisms can be given genes which can have multiple manifestations. For example, a rabbit could have a FurColor gene which can be either "brown" or "white". These genes should affect the survival and breeding of organisms based on how they interact with the environment. For example, white rabbits might survive better in snowy weather because their fur acts as camoflauge. |  | 30 |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Retro
Good | Bad | Actionable Commitments (As a team we will...) | Whose job? | Points | Story
We made some good improvements to how the program was running | There was a lack of cohesion within the team and how work was getting implemented and accomplished | Ensure that we're using the appropriate communication channels and responding to appropriate messages within a reasonable time frame | Xavier | 0 | Change Program Version
Animal move finally being used | There was an overestimation in what people could accomplish | Continue following our internal testing methodology and using them in a similar manner as we have been | Xavier | 2 | Write sprint5.md
We were able to highlight and work towards implementing a full feature with limited hiccoughs | Some things were assigned to early as tasks | Endeavor to plot our sprint goals better and appropriate align tasks so that they allow for independent work without causing delays or issues | Jon | 3 | Update Move
Improved testing and debugging | Lack of communication among team members |  | Ryan | 3 | Organism dying
We finally fixed and implemented some things we talked about for weeks | new features not being implemented into the simulation once completed |  | Dale | 3 | update misc. documentation
|  |  | All | 3 | projectreflections.md
|  |  | jonathan | 2 | tune default values
|  |  | Xavier | 2 | API Documentation
|  |  | Xavier | 2 | Write tutorial.md
|  |  | Dale | 0 | Create a project Documents directory
|  |  | Dale | 2 | Move google documentation int project Documents
|  |  | Ryan | 3 | Limit breeding based upon energy
|  |  | Total: | 25